## Product Backlog
THE APPLICATION DEVELOPMENT PROJECT TOPIC
PRODUCT BACKLOG
Function Name | Feature | Complexity | Planned Code Iteration | In-charge Roll Number | In-charge Full Name | Actual Code Iteration | Status
Database | Feature 1 | Medium | Iteration 1 | ALL |  | Iteration 1 | Done
ERD | Feature 1 | Medium | Iteration 1 | ALL |  | Iteration 1 | Done
Home Page UI | Feature 1 | Simple | Iteration 1 | SE130208 | Hồ Huỳnh Trung Hiếu | Iteration 1 | Done
Login UI | Feature 1 | Simple | Iteration 1 | SE160440 | Đinh Hữu Khang | Iteration 1 | Done
Logout UI | Feature 1 | Simple | Iteration 1 | SE160440 | Đinh Hữu Khang | Iteration 1 | Done
Register UI | Feature 1 | Simple | Iteration 1 | SE62046 | Võ Chí Công | Iteration 1 | Done
Forgot Password UI | Feature 1 | Simple | Iteration 1 | SE62046 | Võ Chí Công | Iteration 1 | N
Cart UI | Feature 1 | Simple | Iteration 1 | SE150580 | Nguyễn Phúc Hậu | Iteration 1 | Done
Search by Category UI | Feature 1 | Simple | Iteration 1 | SE130208 | Hồ Huỳnh Trung Hiếu | Iteration 1 | Done
Edit Profile UI | Feature 1 | Simple | Iteration 1 | SE161104 | Nguyễn Minh Khôi | Iteration 1 | Done
Create Service UI | Feature 1 | Simple | Iteration 1 | SE150580 | Nguyễn Phúc Hậu | Iteration 1 | Done
Update Service UI | Feature 1 | Simple | Iteration 1 | SE62046 | Võ Chí Công | Iteration 1 | N
Remove Service UI | Feature 1 | Simple | Iteration 1 | SE160440 | Đinh Hữu Khang | Iteration 1 | N
View Service Detail UI | Feature 1 | Simple | Iteration 1 | SE130208 | Hồ Huỳnh Trung Hiếu | Iteration 1 | Done
Change Password UI | Feature 1 | Simple | Iteration 1 | SE161104 | Nguyễn Minh Khôi | Iteration 1 | N
Admin Edit User Profile UI | Feature 1 | Simple | Iteration 1 | SE150580 | Nguyễn Phúc Hậu | Iteration 1 | Done
View User List UI | Feature 1 | Simple | Iteration 1 | SE62046 | Võ Chí Công | Iteration 1 | N
View Request List UI | Feature 1 | Simple | Iteration 1 | SE160440 | Đinh Hữu Khang | Iteration 1 | N
View Feedback List UI | Feature 1 | Simple | Iteration 1 | SE130208 | Hồ Huỳnh Trung Hiếu | Iteration 1 | N
Payment UI | Feature 1 | Simple | Iteration 1 | SE161104 | Nguyễn Minh Khôi | Iteration 1 | N
Confirm Service UI | Feature 1 | Simple | Iteration 1 | SE150580 | Nguyễn Phúc Hậu | Iteration 1 | N
Contact Us UI | Feature 1 | Simple | Iteration 1 | SE62046 | Võ Chí Công | Iteration 1 | Done
Login | Feature 2 | Simple | Iteration 2 | SE160440 | Đinh Hữu Khang | Iteration 2 | Done
Logout | Feature 2 | Simple | Iteration 2 | SE160440 | Đinh Hữu Khang | Iteration 2 | Done
Register | Feature 3 | Medium | Iteration 2 | SE62046 | Võ Chí Công | Iteration 2 | Done
Forgot Password | Feature 3 | Medium | Iteration 2 | SE62046 | Võ Chí Công | Iteration 2 | N
Cart | Feature 4 | Medium | Iteration 2 | SE161104 | Nguyễn Minh Khôi | Iteration 2 | N
Search by Category | Feature 5 | Medium | Iteration 2 | SE160440 | Đinh Hữu Khang | Iteration 2 | N
View Profile | Feature 5 | Simple | Iteration 1 | SE161104 | Nguyễn Minh Khôi | Iteration 1 | Done
Edit Profile | Feature 5 | Medium | Iteration 2 | SE130208 | Hồ Huỳnh Trung Hiếu | Iteration 2 | N
Create Service | Feature 6 | Simple | Iteration 2 | SE130208 | Hồ Huỳnh Trung Hiếu | Iteration 2 | N
Update Service | Feature 6 | Medium | Iteration 2 | SE150580 | Nguyễn Phúc Hậu | Iteration 2 | N
Remove Service | Feature 6 | Simple | Iteration 2 | SE62046 | Võ Chí Công | Iteration 2 | N
View Service | Feature 7 | Simple | Iteration 2 | SE160440 | Đinh Hữu Khang | Iteration 2 | N
Change Password | Feature 8 | Simple | Iteration 2 | SE130208 | Hồ Huỳnh Trung Hiếu | Iteration 2 | N
Admin Edit User Profile | Feature 9 | Medium | Iteration 2 | SE161104 | Nguyễn Minh Khôi | Iteration 2 | N
View User List | Feature 10 | Simple | Iteration 2 | SE150580 | Nguyễn Phúc Hậu | Iteration 2 | N
View Request List | Feature 10 | Simple | Iteration 2 | SE150580 | Nguyễn Phúc Hậu | Iteration 2 | N
View Feedback List | Feature 10 | Simple | Iteration 2 | SE62046 | Võ Chí Công | Iteration 2 | N
Create Feedback | Feature 11 | Simple | Iteration 2 | SE62046 | Võ Chí Công | Iteration 2 | N